## RTM
Requirement ID | Module ID | Module | Requirement | Jira Key | Jira Story | Scenario ID(s) | Test Case ID(s) | Manual Coverage | Manual Result | Automation Priority | Automation Status | Notes
REQ-LOGIN-001 | MOD-01 | Authentication / Login | Login page provides username and password fields. | SDQA-3 | User Authentication and Login | TS-LOGIN-001 | TC-LOGIN-001 | Covered | Pass | High | Planned
REQ-LOGIN-002 | MOD-01 | Authentication / Login | Valid credentials authenticate the user successfully. | SDQA-3 | User Authentication and Login | TS-LOGIN-001 | TC-LOGIN-001 | Covered | Pass | High | Planned
REQ-LOGIN-003 | MOD-01 | Authentication / Login | Invalid credentials are rejected. | SDQA-3 | User Authentication and Login | TS-LOGIN-002, TS-LOGIN-003, TS-LOGIN-004 | TC-LOGIN-002, TC-LOGIN-003, TC-LOGIN-004 | Covered | Pass | High | Planned
REQ-LOGIN-004 | MOD-01 | Authentication / Login | Login is prevented when username is missing. | SDQA-3 | User Authentication and Login | TS-LOGIN-005, TS-LOGIN-007 | TC-LOGIN-005, TC-LOGIN-007 | Covered | Pass | High | Planned
REQ-LOGIN-005 | MOD-01 | Authentication / Login | Login is prevented when password is missing. | SDQA-3 | User Authentication and Login | TS-LOGIN-006, TS-LOGIN-007 | TC-LOGIN-006, TC-LOGIN-007 | Covered | Pass | High | Planned
REQ-LOGIN-006 | MOD-01 | Authentication / Login | Authentication failures display an appropriate error message. | SDQA-3 | User Authentication and Login | TS-LOGIN-002, TS-LOGIN-003, TS-LOGIN-004, TS-LOGIN-005, TS-LOGIN-006, TS-LOGIN-007, TS-LOGIN-008 | TC-LOGIN-002, TC-LOGIN-003, TC-LOGIN-004, TC-LOGIN-005, TC-LOGIN-006, TC-LOGIN-007, TC-LOGIN-008 | Covered | Pass | High | Planned
REQ-LOGIN-007 | MOD-01 | Authentication / Login | Locked-out users cannot access the application. | SDQA-3 | User Authentication and Login | TS-LOGIN-008 | TC-LOGIN-008 | Covered | Pass | High | Planned
REQ-PROD-001 | MOD-02 | Product Listing & Sorting | Products are displayed after successful authentication. | SDQA-4 | Product Listing and Sorting | TS-PROD-001 | TC-PROD-001 | Covered | Pass | High | Planned
REQ-PROD-002 | MOD-02 | Product Listing & Sorting | Each product displays identifying information. | SDQA-4 | Product Listing and Sorting | TS-PROD-002 | TC-PROD-002 | Covered | Pass | Medium | Planned
REQ-PROD-003 | MOD-02 | Product Listing & Sorting | A product can be added from the product listing. | SDQA-4 | Product Listing and Sorting | TS-PROD-003, TS-PROD-005 | TC-PROD-003, TC-PROD-005 | Covered | Pass | High | Planned
REQ-PROD-004 | MOD-02 | Product Listing & Sorting | An added product can be removed from the product listing. | SDQA-4 | Product Listing and Sorting | TS-PROD-004, TS-PROD-006 | TC-PROD-004, TC-PROD-006 | Covered | Pass | High | Planned
REQ-PROD-005 | MOD-02 | Product Listing & Sorting | The cart indicator reflects the number of selected products. | SDQA-4 | Product Listing and Sorting | TS-PROD-003, TS-PROD-004, TS-PROD-005, TS-PROD-006 | TC-PROD-003, TC-PROD-004, TC-PROD-005, TC-PROD-006 | Covered | Pass | High | Planned
REQ-PROD-006 | MOD-02 | Product Listing & Sorting | Products can be sorted by name A to Z. | SDQA-4 | Product Listing and Sorting | TS-PROD-007 | TC-PROD-007 | Covered | Pass | Medium | Planned
REQ-PROD-007 | MOD-02 | Product Listing & Sorting | Products can be sorted by name Z to A. | SDQA-4 | Product Listing and Sorting | TS-PROD-008 | TC-PROD-008 | Covered | Pass | Medium | Planned
REQ-PROD-008 | MOD-02 | Product Listing & Sorting | Products can be sorted by price low to high. | SDQA-4 | Product Listing and Sorting | TS-PROD-009 | TC-PROD-009 | Covered | Pass | Medium | Planned
REQ-PROD-009 | MOD-02 | Product Listing & Sorting | Products can be sorted by price high to low. | SDQA-4 | Product Listing and Sorting | TS-PROD-010 | TC-PROD-010 | Covered | Pass | Medium | Planned
REQ-PDETAIL-001 | MOD-03 | Product Details | An individual product details page can be opened from the product listing. | SDQA-5 | Product Details | TS-PDETAIL-001 | TC-PDETAIL-001 | Covered | Pass | Medium | Planned
REQ-PDETAIL-002 | MOD-03 | Product Details | The details page corresponds to the selected product. | SDQA-5 | Product Details | TS-PDETAIL-002, TS-PDETAIL-006 | TC-PDETAIL-002, TC-PDETAIL-006 | Covered | Pass | High | Planned
REQ-PDETAIL-003 | MOD-03 | Product Details | A product can be added to the cart from its details page. | SDQA-5 | Product Details | TS-PDETAIL-003 | TC-PDETAIL-003 | Covered | Pass | High | Planned
REQ-PDETAIL-004 | MOD-03 | Product Details | An added product can be removed from its details page. | SDQA-5 | Product Details | TS-PDETAIL-004 | TC-PDETAIL-004 | Covered | Pass | High | Planned
REQ-PDETAIL-005 | MOD-03 | Product Details | The user can return from product details to the product listing. | SDQA-5 | Product Details | TS-PDETAIL-005 | TC-PDETAIL-005 | Covered | Pass | Medium | Planned
REQ-CART-001 | MOD-04 | Shopping Cart | The cart displays products added by the user. | SDQA-6 | Shopping Cart | TS-CART-001, TS-CART-002 | TC-CART-001, TC-CART-002 | Covered | Pass | High | Planned
REQ-CART-002 | MOD-04 | Shopping Cart | Cart item information corresponds to the selected products. | SDQA-6 | Shopping Cart | TS-CART-002, TS-CART-003 | TC-CART-002, TC-CART-003 | Covered | Pass | High | Planned
REQ-CART-003 | MOD-04 | Shopping Cart | Products can be removed directly from the shopping cart. | SDQA-6 | Shopping Cart | TS-CART-004, TS-CART-005 | TC-CART-004, TC-CART-005 | Covered | Pass | High | Planned
REQ-CART-004 | MOD-04 | Shopping Cart | The user can return from the cart to product browsing. | SDQA-6 | Shopping Cart | TS-CART-006 | TC-CART-006 | Covered | Pass | Medium | Planned
REQ-CART-005 | MOD-04 | Shopping Cart | The user can proceed from the cart to checkout. | SDQA-6 | Shopping Cart | TS-CART-007 | TC-CART-007 | Covered | Pass | High | Planned
REQ-CART-006 | MOD-04 | Shopping Cart | Cart contents remain consistent during normal navigation unless changed or reset. | SDQA-6 | Shopping Cart | TS-CART-005, TS-CART-008 | TC-CART-005, TC-CART-008 | Covered | Pass | High | Planned
REQ-CHKINFO-001 | MOD-05 | Checkout — Customer Information | The checkout information page provides a First Name field. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-001, TS-CHKINFO-006 | TC-CHKINFO-001, TC-CHKINFO-006 | Covered | Pass | Medium | Planned
REQ-CHKINFO-002 | MOD-05 | Checkout — Customer Information | The checkout information page provides a Last Name field. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-001, TS-CHKINFO-006 | TC-CHKINFO-001, TC-CHKINFO-006 | Covered | Pass | Medium | Planned
REQ-CHKINFO-003 | MOD-05 | Checkout — Customer Information | The checkout information page provides a Postal Code field. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-001, TS-CHKINFO-006 | TC-CHKINFO-001, TC-CHKINFO-006 | Covered | Pass | Medium | Planned
REQ-CHKINFO-004 | MOD-05 | Checkout — Customer Information | Checkout progression is prevented when required customer information is missing. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-002, TS-CHKINFO-003, TS-CHKINFO-004, TS-CHKINFO-005, TS-CHKINFO-008, TS-CHKINFO-009 | TC-CHKINFO-002, TC-CHKINFO-003, TC-CHKINFO-004, TC-CHKINFO-005, TC-CHKINFO-008, TC-CHKINFO-009 | Covered | Pass | High | Planned
REQ-CHKINFO-005 | MOD-05 | Checkout — Customer Information | An appropriate validation message is displayed when required information is missing. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-002, TS-CHKINFO-003, TS-CHKINFO-004, TS-CHKINFO-005, TS-CHKINFO-008, TS-CHKINFO-009 | TC-CHKINFO-002, TC-CHKINFO-003, TC-CHKINFO-004, TC-CHKINFO-005, TC-CHKINFO-008, TC-CHKINFO-009 | Covered | Pass | High | Planned
REQ-CHKINFO-006 | MOD-05 | Checkout — Customer Information | Valid required information allows the user to continue to checkout overview. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-001 | TC-CHKINFO-001 | Covered | Pass | High | Planned
REQ-CHKINFO-007 | MOD-05 | Checkout — Customer Information | Cancel returns the user from checkout information to the shopping cart. | SDQA-7 | Checkout — Customer Information | TS-CHKINFO-007 | TC-CHKINFO-007 | Covered | Pass | High | Planned
REQ-CHKOV-001 | MOD-06 | Checkout — Order Overview | The checkout overview displays products included in the order. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-001 | TC-CHKOV-001 | Covered | Pass | High | Planned
REQ-CHKOV-002 | MOD-06 | Checkout — Order Overview | The checkout overview displays pricing corresponding to selected products. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-002 | TC-CHKOV-002 | Covered | Pass | High | Planned
REQ-CHKOV-003 | MOD-06 | Checkout — Order Overview | The checkout overview displays a correct item subtotal. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-003, TS-CHKOV-005 | TC-CHKOV-003, TC-CHKOV-005 | Covered | Pass | High | Planned
REQ-CHKOV-004 | MOD-06 | Checkout — Order Overview | The checkout overview displays tax separately. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-004, TS-CHKOV-005 | TC-CHKOV-004, TC-CHKOV-005 | Covered | Pass | Medium | Planned
REQ-CHKOV-005 | MOD-06 | Checkout — Order Overview | The checkout overview displays a final total consistent with subtotal plus tax. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-005 | TC-CHKOV-005 | Covered | Pass | High | Planned
REQ-CHKOV-006 | MOD-06 | Checkout — Order Overview | The user can finish the order from checkout overview. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-006 | TC-CHKOV-006 | Covered | Pass | High | Planned
REQ-CHKOV-007 | MOD-06 | Checkout — Order Overview | The user can cancel from checkout overview without completing the order. | SDQA-8 | Checkout — Order Overview | TS-CHKOV-007 | TC-CHKOV-007 | Covered | Pass | High | Planned
REQ-ORDER-001 | MOD-07 | Order Completion | A dedicated order-completion page is displayed after a valid checkout is finished. | SDQA-9 | Order Completion | TS-ORDER-001 | TC-ORDER-001 | Covered | Pass | High | Planned
REQ-ORDER-002 | MOD-07 | Order Completion | Successful order completion is clearly communicated to the user. | SDQA-9 | Order Completion | TS-ORDER-002 | TC-ORDER-002 | Covered | Pass | High | Planned
REQ-ORDER-003 | MOD-07 | Order Completion | The user can return to the Products inventory after order completion. | SDQA-9 | Order Completion | TS-ORDER-003 | TC-ORDER-003 | Covered | Pass | Medium | Planned
REQ-NAV-001 | MOD-08 | Navigation, Menu & Session | An authenticated user can open the application navigation menu. | SDQA-10 | Navigation, Menu and Session | TS-NAV-001 | TC-NAV-001 | Covered | Pass | Medium | Planned
REQ-NAV-002 | MOD-08 | Navigation, Menu & Session | All Items navigates the user to the Products inventory. | SDQA-10 | Navigation, Menu and Session | TS-NAV-002 | TC-NAV-002 | Covered | Pass | Medium | Planned
REQ-NAV-003 | MOD-08 | Navigation, Menu & Session | About navigates to the configured external destination. | SDQA-10 | Navigation, Menu and Session | TS-NAV-003 | TC-NAV-003 | Covered | Pass | Low | Planned | External destination may be less stable than core application flows.
REQ-NAV-004 | MOD-08 | Navigation, Menu & Session | Reset App State clears the user's current application state. | SDQA-10 | Navigation, Menu and Session | TS-NAV-004 | TC-NAV-004 | Covered | Pass | High | Planned
REQ-NAV-005 | MOD-08 | Navigation, Menu & Session | An authenticated user can log out successfully. | SDQA-10 | Navigation, Menu and Session | TS-NAV-005 | TC-NAV-005 | Covered | Pass | High | Planned
REQ-NAV-006 | MOD-08 | Navigation, Menu & Session | A logged-out user cannot regain normal authenticated access without logging in again. | SDQA-10 | Navigation, Menu and Session | TS-NAV-006 | TC-NAV-006 | Covered | Pass | High | Planned

## Summary
SauceDemo Requirements Traceability Matrix — Summary
KPI | Value |  | How to use this workbook
Total Requirements | 50 |  | The RTM is the master traceability view: Requirement → Jira Story → Scenario → Test Case → Manual Result → Automation plan. Store this file in GitHub under reports/traceability/. Update any Manual Result that differs from Pass and change Automation Status from Planned to Automated as Selenium coverage is added.
Mapped Requirements | 50
Manual Coverage | 100%
Passed Requirements | 50
High Automation Priority | 34
Module ID | Module | Requirements | Test Cases | Jira Key
MOD-01 | Authentication / Login | 7 | 8 | SDQA-3
MOD-02 | Product Listing & Sorting | 9 | 10 | SDQA-4
MOD-03 | Product Details | 5 | 6 | SDQA-5
MOD-04 | Shopping Cart | 6 | 9 | SDQA-6
MOD-05 | Checkout — Customer Information | 7 | 9 | SDQA-7
MOD-06 | Checkout — Order Overview | 7 | 7 | SDQA-8
MOD-07 | Order Completion | 3 | 3 | SDQA-9
MOD-08 | Navigation, Menu & Session | 6 | 6 | SDQA-10

## Reference
Module ID | Module | Jira Key | Jira Story | Zephyr Test Cycle | Test Case Count | Project Note
MOD-01 | Authentication / Login | SDQA-3 | User Authentication and Login | Login Functional Test Cycle | 8 | Jira keys follow the project sequence used during this portfolio. If your final Navigation story key differs from SDQA-10, update MOD-08 here and the MOD-08 Jira Key cells in the RTM sheet.
MOD-02 | Product Listing & Sorting | SDQA-4 | Product Listing and Sorting | Product Listing Functional Test Cycle | 10
MOD-03 | Product Details | SDQA-5 | Product Details | Product Details Functional Test Cycle | 6
MOD-04 | Shopping Cart | SDQA-6 | Shopping Cart | Shopping Cart Functional Test Cycle | 9
MOD-05 | Checkout — Customer Information | SDQA-7 | Checkout — Customer Information | Checkout Customer Information Functional Test Cycle | 9
MOD-06 | Checkout — Order Overview | SDQA-8 | Checkout — Order Overview | Checkout Order Overview Functional Test Cycle | 7
MOD-07 | Order Completion | SDQA-9 | Order Completion | Order Completion Functional Test Cycle | 3
MOD-08 | Navigation, Menu & Session | SDQA-10 | Navigation, Menu and Session | Navigation and Session Functional Test Cycle | 6